## Executive Summary
Project Request
Project Name: | Japan eMarketplace
Business Owner: | Tomoko Iwasaki
Function Head: | Tomoko Iwasaki
Susponsor (optional):
Brand(s): | UGG/HOKA/TEVA
Channel(s): | eCom
Department: | eCom
Impacted cross-functions and key stakeholders: | Finance - Ricky/ Supply Chain & Operation - Kaz/ Accounting - Jennifer/ Global DTC - Angela, Legal -Andrew , Security -Chop , Merch&Allocation -Endo, Planning(INV) -Shane, Tech Delivery Team ,
High Level Scope and Objective: | We need to build a connector between our system & marketplace in order to; 1. Connect catalog master data, image. Part of product catalog for localized data/Pricing information from SFCC (salesforce) 2. Connect transactional data . Trans shipping data to DOMS/Hitachi, marketplace to Oracle for finance data 3. Configure two customer accounts in our system to manage marketplace inventory ,alocation and inventory owned by Deckres, operation delivery by 3PL Hitachi 4. Consolidated reporting for accounting/fianance. 5. Potential Additional Connection between marketplace and Logisteed for the dropship model out of Decekrs System . (Need 1 resource from their side to make sure timeline control and quality) ***Connector should be ideally the global which is capable to support multiple markets/multiple platforms
Executive Summary: | As a business owner and scale eCom Japan business, we would like to set up our systems, processes and teams to enable an onlinep partner program in Japan. So that we can partner with various marketplaces to sell our products across a wider base of clients with a better margin. The expected results in the next 3 years is 23M USD.
Business Case: | Open 2 of the major marketplaces - Rakuten & ZOZOTOWN. -Open UGG on Rakuten and ZOZOTOWN for Full Price Business -Open HOKA on ZOZOTOWN for Lifestyle expansion -Open TEVA on Rakuten for Outlet Business (Inventory Liquidation) -Rakuten is Dropship Model -ZOZOTOWN is a hybrid of Dropship and Marketplace Model (site management by deckers, transaction and shipment by Zozotown) -Connector pricing is usually around 54K USD annually for the size of the business it's ttl cost for connector (maybe increased if transaction +++) - Pre-sell scenario owned by marketplace, operation by Decekrs - Deckers Ecom team owns platforms product onshelf/off, product attributes etc ***Overall, input/dudget estimation in these business cases covered in commision, additonal logistic and mkt fee , running cost
Benefits: | 1. 23M USD incremental revenue in the next 3 years/ Flat in OI%. 2. More accessible touchpoints for the consumers 3. Larger reach by leveraging the 3rd party platform base 4. Better marketplace management
Business Plan (Optional) : | Additional Marketplace such as Yahoo/Amazon
Requested Go-live Date: | Ideal Project Go-Live Date : By the end of FY26

## Service Model
Business Incremental
*Please ignore FY26 as this wont likely to happen. Ive included incremental 23M USD between FY27 - FY29 for 3 years in the business case.
Service Model Differences between Rakuten and ZOZOTOWN:
Relevant Costs:
-Comission Fee (9% for Rakuten/28% for ZOZOTOWN)
-Connector platform running cost 54K USD annually (Incremental by # of transaction)
-Warehouse Outbound freight : Already reflected in the gross margin impact so no further net incremental cost for this