## Sheet1
| EY | Deckers IT
Trial Balance Closed Loop Automation |  |  | R = Responsible
Design workshops |  |  | A = Accountable
Define scheduling to initiate the extraction of TBs from Oracle | A | R | Deckers Tax will be consulted and informed on all tasks
Define trial balance extraction process (record selection and file format) | A | R
Define trial balance file storage process | A | R
Define API application rules required to process trial balance
Dataset | R | A
Subconsolidation (report level) | R | A
OTP Components ( PTBI, book balances, perm diffs, temp diffs) | R | A
Bridge Parameters (class/subclass, profile, rules) | R | A
Define monitoring and error handling process | R | A
Gain access to source systems | A | R
Build/Configure scheduling application | A | R
Build API application to process Trial Balance
Configure OTP system parameters | R | A
Transformation to convert TB to Bridge format | R | A
Build API application rules for OTP bridge import | R | A
Build monitoring and error handling process | R | A
System unit testing/system itegration testing | A | R
User Acceptance Testing | A | R
User Acceptance Testing support | R | A
Process documentation | R | A
Trial Balance Closed loop training material | R | A
Conduct Trial Balance Closed Loop training | R | A
JE Closed Loop Automation
Design workshops
Define scheduling for JE submission to Oracle (triggered by user, or scheduled) | A | R
Define JE extraction process (record selection and file format) from OTP | R | A
Define API application rules required to process journal entries
Dataset | R | A
Subconsolidation (report level) | R | A
Define JE file storage process | A | R
Define Oracle JE posting process | A | R
Define monitoring and error handling process | R | A
Gain access to source systems | A | R
Build/Configure scheduling application | A | R
Build API application to process Journal Entries
Configure OTP system parameters | R | A
Build API application rules for OTP JE extraction | R | A
Build monitoring and error handling process | R | A
Transformation to convert OTP JE to Oracle GL format | R | A
Build process to import Journal Entries into Oracle | A | R
System unit testing/system itegration testing | A | R
User Acceptance Testing | A | R
User Acceptance Testing support | R | A
Process documentation | R | A
Journal Entry Closed loop training material | R | A
Conduct Journal Entry Closed Loop training | R | A